Construction Schedule:

Haskell- Sylmar Transmision Line 2 Project

#### Construction Contacts

Project Manager: Jeremy Fabregas | 213-367-0092 | jeremy.fabregas@ladwp.com

Community Liaison: Christina Holland | 213-367-1076 | christina.holland@ladwp.com

#### Estimated Milestone Dates – Sylmar Phase

- Grading: - August 2022

- Wire Removal: - Late August to Early October 2022

- Existing Structure and Foundation Removal: - Second week of September 2022 Foundation installs: - Second and third week of October 2022

- Monopole Installation: - First and second week of November 2022

- Wire installation: - October and December 2022 (Estimated Crossing Schedule below)

| #### Crossing | #### City | #### Wire Demo Dates | #### Wire Install Dates |
| --- | --- | --- | --- |
| #### San Fernando Rd. | #### Sylmar | #### 8/29/22 – 8/29/22 | #### 10/18/22 – 10/28/22 |
| #### I-5 | #### Sylmar | #### 9/30/22 – 10/3/22 | #### 10/18/22 – 10/28/22 |
| #### Golden State Rd. | #### Sylmar | #### 9/30/22 – 10/3/22 | #### 10/18/22 – 10/28/22 |
| #### Sepulveda Blvd. | #### Sylmar | #### 9/30/22 – 10/3/22 | #### 10/18/22 – 10/28/22 |
| #### Filbert St. | #### Sylmar | #### 10/9/22 – 10/9/22 | #### 12/6/22 – 12/30/22 |
| #### I-210 | #### Sylmar | #### 10/9/22 – 10/9/22 | #### 12/6/22 – 12/30/22 |
| #### Foothill Blvd. | #### Sylmar | #### 10/9/22 – 10/9/22 | #### 12/6/22 – 12/30/22 |