**Construction Schedule**:

Haskell- Sylmar Transmision Line 2 Project

**Construction Contacts**

**Project Manager:** Jeremy Fabregas | 213-367-0092 | jeremy.fabregas@ladwp.com

**Community Liaison:** Christina Holland | 213-367-1076 | christina.holland@ladwp.com

**Estimated Milestone Dates – Sylmar Phase**

* **Grading**: - August 2022
* **Wire Removal**: - Late August to Early October 2022
* **Existing Structure and Foundation Removal**: - Second week of September 2022 **Foundation installs**: - Second and third week of October 2022
* **Monopole Installation**: - First and second week of November 2022
* **Wire installation**: - October and December 2022 (Estimated Crossing Schedule below)

|  |  |  |  |
| --- | --- | --- | --- |
| **Crossing** | **City** | **Wire Demo Dates** | **Wire Install Dates** |
| San Fernando Rd. | Sylmar | 8/29/22 – 8/29/22 | 10/18/22 – 10/28/22 |
| I-5 | Sylmar | 9/30/22 – 10/3/22 | 10/18/22 – 10/28/22 |
| Golden State Rd. | Sylmar | 9/30/22 – 10/3/22 | 10/18/22 – 10/28/22 |
| Sepulveda Blvd. | Sylmar | 9/30/22 – 10/3/22 | 10/18/22 – 10/28/22 |
| Filbert St. | Sylmar | 10/9/22 – 10/9/22 | 12/6/22 – 12/30/22 |
| I-210 | Sylmar | 10/9/22 – 10/9/22 | 12/6/22 – 12/30/22 |
| Foothill Blvd. | Sylmar | 10/9/22 – 10/9/22 | 12/6/22 – 12/30/22 |